## Sheet1
ESTIMATE CHAMPION
Task Details and Time Estimation
S.No | Task Details | Start Date | End Date | No Of Hours | Assigned To | Status | Comment
1 | User and Client Creation, email has to be validated and a email has to be sent along with username and password | 2018-02-27 | 2018-02-28 | 12 | Sai
2 | User or admin can login using their Email | 2018-02-27 | 2018-02-27 | 2 | Sai | Complated
3 | Add Demo in client details, number of users have access field. Auto fill the start and end date for demo, auto fill the number of days for demo and decrement the number of days automatically for each day | 2018-02-28 | 2018-03-02 | 18 | Sai | Complated
4 | Add field as Data_Type varchar(10) in all master field and work table. And add the value as Demo if the client is in Demo days | 2018-02-28 | 2018-02-28 | 6 | Sai | Complated
5 | For User login, we have to show number of days pending to end the demo | 2018-03-05 | 2018-03-05 | 3 | Sai | Complated
6 | Work description select from Previous | 2018-03-05 | 2018-03-05 | 2 | Sai
7 | Client and user restrictions while login, also restricting the number of users | [5 empty] | Pending Estimation